## README
GENRANQ — Build Plan Workbook
Developer source-of-truth: modules, backlog, database schema, integrations, roadmap, pricing & cost estimate.
Sheet | What it contains / how to use
Module Catalog | All 40+ modules with area, priority, complexity, phase and owner. Filter by phase to scope a release.
Feature Backlog | Epics → features with MoSCoW priority and story points. Points roll up per epic (live formula).
Database Schema | Core tables, key columns, types and notes. Blue = primary key, teal = foreign key.
API Integrations | Every external provider (incl. Claude/OpenAI/Perplexity/Gemini, PSI, Stripe): purpose, auth, quota, phase.
Roadmap | Phase-by-phase plan with durations, squads and dependencies; total weeks computed.
Audit Checklist | 50+ automated SEO checks mapped to data source, severity & owner; feeds the SEO Action Plan.
Pricing Matrix | Feature availability across Essentials / Advanced / Enterprise tiers (from reference screenshots).
Cost Estimate | Effort by phase → hours → cost. EDIT ONLY the blue input cells; totals are formulas.
Legend
Blue cell | Editable input (change these)
Green | Done / included / P1
Amber | In progress / partial / P2
Red / — | Not included / blocked

## Module Catalog
Module Catalog
40+ modules grouped by platform area. Priority P1 (must) → P3 (later). Complexity S/M/L/XL.
# | Area | Module | Description | Priority | Complexity | Phase
1 | Dashboard | Overview & KPIs | Cross-module KPIs, activity feed, quick actions | P1 | M | 0
2 | Dashboard | Tasks | Task list/board tied to projects | P1 | M | 0
3 | Dashboard | Time Tracking | Timers, timesheets, billable hours, productivity reports | P1 | M | 0
4 | Dashboard | Projects | Projects, templates, multi-assignee | P1 | M | 0
5 | Dashboard | Team | Departments, roles, permissions | P1 | M | 0
6 | SEO | Rank Tracker | Keyword rank tracking, history, reports | P1 | L | 1
7 | SEO | SEO Audit | Technical/on-page/content scoring engine + PDF | P1 | XL | 1
8 | SEO | Screaming Frog Automation | Scheduled crawls, issue detection, crawl diff | P1 | L | 1
9 | SEO | Ahrefs Integration | Domain/keyword/backlink data ingest | P2 | M | 2
10 | SEO | Semrush Integration | Keyword/position/toxic data ingest | P2 | M | 2
11 | SEO | Keywords | Research, clustering, difficulty, gaps | P2 | L | 1
12 | SEO | Rankings | Aggregated ranking dashboards | P1 | M | 1
13 | SEO | Backlinks (CRM) | Paid/free DB, live/removed, files, metrics | P1 | XL | 2
14 | SEO | Backlink Marketplace | Buy/sell, publisher & advertiser, orders | P3 | XL | 6
15 | Local SEO | GMB/GBP Audit | Profile completeness, NAP, knowledge panel | P1 | L | 3
16 | Local SEO | Category Finder | Primary/secondary + competitor categories | P2 | M | 3
17 | Local SEO | Review Audit | Volume, sentiment, trends, AI responses | P1 | L | 3
18 | Local SEO | Post Audit | Posting cadence & content analysis | P2 | M | 3
19 | Local SEO | Local Scan | Multi-competitor local comparison | P2 | L | 3
20 | Local SEO | Rank / Teleport (geo-grid) | Grid-based Maps/Local Finder rank + heatmap | P1 | XL | 3
21 | Local SEO | Competitor Research | Discovery, gaps, local score | P2 | L | 3
22 | Local SEO | Website ↔ GBP Audit | Consistency scoring across site & profile | P2 | M | 3
23 | Local SEO | Chrome Extension | Audit buttons on Search/Maps/GBP | P3 | L | 6
24 | AI Studio | Blog Generator | Brief→outline→draft→schema→publish | P1 | L | 4
25 | AI Studio | News Generator | Topic discovery, drafting, scheduling | P2 | M | 4
26 | AI Studio | Whitepaper Generator | Long-form + charts + PDF | P3 | L | 4
27 | AI Studio | Publication Generator | Thought-leadership articles | P3 | M | 4
28 | AI Studio | Playbook Generator | SOPs/playbooks, versioned, export | P3 | M | 4
29 | AI Studio | Website Generator | Landing/service/location pages, meta, schema | P2 | XL | 4
30 | AI Studio | Social Posts | Per-platform post + caption + hashtags | P1 | M | 4
31 | AI Studio | GMB Posts | Offer/update/event posts + images | P1 | M | 4
32 | AI Studio | Image Generator | Branded images, multiple sizes, bulk | P2 | L | 4
33 | Automation | Content Automation | Bulk generate→approve→schedule→publish | P1 | L | 5
34 | Automation | SEO Automation | Scheduled audits/crawls/rank + alerts | P1 | M | 5
35 | Automation | GMB Automation | Bulk GBP posts across locations | P2 | M | 5
36 | Automation | Social Automation | Recurring/campaign scheduling | P1 | M | 5
37 | Automation | Report Automation | Scheduled white-label PDF/Excel reports | P1 | M | 5
38 | Social | Social Accounts | Connect Meta/LinkedIn/X, multi-account | P1 | M | 5
39 | Social | Content Calendar | Unified calendar & approvals | P1 | M | 5
40 | Social | Analytics | Engagement & performance tracking | P2 | M | 5
41 | Leads/CRM | Leads & Forms | Capture, dedupe, status, assignment | P1 | L | 6
42 | Leads/CRM | Attribution | UTM/source/campaign attribution models | P2 | L | 6
43 | Leads/CRM | HubSpot | Two-way contact/deal/form sync | P2 | M | 6
44 | Leads/CRM | Calendly | Booking links & lead→booking tracking | P3 | S | 6
45 | Team & Admin | Approvals | Content/permission approval chains | P1 | M | 0
46 | Team & Admin | Microsoft Teams | Notifications & channels | P2 | S | 6
47 | Team & Admin | White-Label | Per-tenant branding & domains | P2 | M | 6
48 | Team & Admin | Credential Vault | Encrypted supplier/site creds, audited | P1 | L | 2
49 | Team & Admin | Integrations Hub | OAuth connector management | P1 | M | 1
50 | AI Engine | AI Provider Hub | Connect Claude, OpenAI/ChatGPT, Perplexity, Gemini + others; routing & fallback | P1 | L | 4
51 | AI Engine | Prompt Library | Embedded prompts + custom prompts, variables, versioning | P1 | M | 4
52 | AI Engine | Skills System | Inbuilt skills + custom skills (reusable instruction+tool packs) | P1 | L | 4
53 | AI Engine | AI Agent Teams | Compose multi-agent workflows (research→outline→write→edit) | P2 | XL | 4
54 | AI Engine | AI Cost & Usage | Per-provider token cost, quotas, usage analytics | P2 | M | 4
55 | SEO | PageSpeed / Core Web Vitals | Google PSI: desktop/mobile, LCP/CLS/INP, history, fixes | P1 | M | 1
56 | SEO | Search Console Audit | GSC coverage/index issues ingest into audit | P1 | M | 1
57 | SEO | Automated Audit Checklist | 50+ checks mapped to data source + owner (from checklist) | P1 | XL | 1
58 | SEO | Competitor Audit (site & page) | Whole-site + page-to-page comparison vs competitors | P2 | XL | 1
59 | SEO | SEO Action Plan | Auto-generate prioritized SEO plan from audit findings | P1 | L | 1
60 | AI Studio | Landing Page Generator | Landing/service/location page copy + meta + schema | P1 | L | 4
61 | AI Studio | Topical Map | Parent/child keyword clustering → topical map | P1 | L | 4
62 | AI Studio | Content Plan Builder | Pillar+cluster plan, briefs, internal-link map | P1 | L | 4
63 | AI Studio | ReleVink AI (placement finder) | Keyword/anchor → find relevant pages for links | P2 | L | 6
64 | Leads/CRM | Form Builder | Contact & custom forms, embeddable, validation | P1 | M | 6
65 | Leads/CRM | Form Connectors | Connect external forms/webhooks for lead capture | P2 | M | 6
66 | Leads/CRM | Onboarding / Profiling | Qualify leads (who/what/source) on signup | P2 | S | 6
67 | Free Tools | Domain Age Checker | Check domain history in seconds | P2 | S | 6
68 | Free Tools | Broken Link Checker | Find & fix broken links | P2 | S | 6
69 | Free Tools | Link Analyzer | Analyze a site's link profile | P2 | M | 6
70 | Free Tools | Backlink Monitoring Tool | Track active backlinks 24/7 (public) | P2 | M | 6
71 | Free Tools | Dofollow/Nofollow Checker | Verify link rel attributes | P3 | S | 6
72 | Free Tools | Website Finder (extension) | Find guest-post sites from Chrome | P3 | M | 6
73 | Marketplace | Services Catalog | Link Building, Guest Post, Digital PR, Niche Edits, Content, Brand Mentions, SEO Reseller | P2 | L | 6
74 | Marketplace | Listings & Filters | DA/DR/AS, traffic, CF/TF, spam, category, country, price | P2 | L | 6
75 | Marketplace | Cart & Orders | Guest post / link insertion orders, TAT, sample/report | P2 | L | 6
76 | Marketplace | Wallet & Balance | Add funds, balance, invoices, payouts | P2 | M | 6

## Feature Backlog
Feature Backlog
Epics → features. MoSCoW = Must/Should/Could. Points roll up per epic (SUMIF).
ID | Epic | Feature | MoSCoW | Points | Acceptance / notes
F-001 | Platform | Multi-tenant org + RBAC roles | Must | 8 | Owner/Admin/Manager/Staff/Client; RLS isolation
F-002 | Platform | Auth: SSO/OIDC + JWT + MFA | Must | 5 | Refresh rotation, step-up auth for vault
F-003 | Platform | Projects, tasks, time tracking | Must | 8 | Timers, timesheets, billable flag, reports
F-004 | Platform | Job queue + worker fleet + scheduler | Must | 8 | Retry/backoff, rate-limit tokens, DLQ
F-005 | Platform | Activity log / audit trail | Must | 3 | Immutable, filterable, per-tenant
F-006 | SEO Audit | Crawl orchestration | Must | 13 | Politeness, robots, dedupe, link graph
F-007 | SEO Audit | Rule engine + weighted score | Must | 13 | Technical/on-page/content/off-page
F-008 | SEO Audit | Priority ranking of issues | Must | 5 | impact×prevalence×effort-inverse
F-009 | SEO Audit | AI recommendations (Claude) | Should | 5 | Top issues → fix guidance
F-010 | SEO Audit | PDF/Excel export + white-label | Must | 5 | Branded, scheduled
F-011 | Rank Tracker | Keyword rank checks + history | Must | 8 | Daily/weekly/monthly; ClickHouse
F-012 | Rank Tracker | SERP feature & competitor tracking | Should | 5 | Featured snippets, local pack
F-013 | Backlink CRM | Backlink DB + classification | Must | 8 | paid/free, dofollow/nofollow/sponsored/ugc
F-014 | Backlink CRM | Supplier CRM + email management | Must | 8 | Profiles, price lists, comms history
F-015 | Backlink CRM | Live/Removed verification job | Must | 13 | Headless fallback, evidence, history
F-016 | Backlink CRM | Semrush toxic scoring + workflow | Must | 8 | Advisory only; human disavow gate
F-017 | Backlink CRM | File management (invoices/reports) | Should | 5 | Linked client→project→supplier→backlink
F-018 | Backlink CRM | Credential vault (encrypted) | Must | 8 | KMS, masked, audited, no secrets in export
F-019 | Backlink CRM | Backlink dashboard + KPIs | Must | 5 | Live/removed/toxic, live-rate, retention
F-020 | Local SEO | Geo-grid rank (Teleport) | Must | 13 | Grid gen, geo SERP, heatmap, metrics
F-021 | Local SEO | GMB/GBP audit + NAP | Must | 8 | Completeness, same-address, knowledge panel
F-022 | Local SEO | Review audit + AI responses | Must | 8 | Sentiment, trends, competitor compare
F-023 | Local SEO | Category finder | Should | 5 | Primary/secondary + competitor categories
F-024 | Local SEO | Website↔GBP consistency | Should | 5 | Field matching + score
F-025 | AI Studio | Content state machine | Must | 8 | draft→generated→review→approve→publish
F-026 | AI Studio | Blog/news/social/GMB generators | Must | 13 | Brief templates per type, brand voice
F-027 | AI Studio | Image generation + sizes | Should | 8 | Branded, bulk
F-028 | AI Studio | Approval workflow | Must | 5 | Role-gated, reject-with-notes
F-029 | Social | Connectors: Meta/LinkedIn/X | Must | 13 | OAuth, publish, idempotent
F-030 | Social | Content calendar + scheduler | Must | 8 | Multi-account, recurring, campaigns
F-031 | Social | Analytics ingest | Should | 5 | Engagement, failed-post alerts
F-032 | Leads/CRM | Lead capture + dedupe | Must | 8 | Forms, FB/LI lead ads, webhooks
F-033 | Leads/CRM | Attribution models | Should | 5 | first/last/linear touch
F-034 | Leads/CRM | HubSpot sync | Should | 8 | Two-way where supported
F-035 | Leads/CRM | Calendly booking tracking | Could | 3 | lead→booking attribution
F-036 | Reporting | Looker Studio + custom builder | Should | 8 | Drag-drop, schedule, white-label
F-037 | Integrations | Teams notifications | Should | 3 | Alerts, reports, approvals
F-038 | Integrations | Accounting add-on (Xero/MYOB/QB) | Could | 8 | Optional tier
F-039 | AI Engine | Multi-provider gateway | Must | 13 | Claude/OpenAI/Perplexity/Gemini; routing, fallback, keys in vault
F-040 | AI Engine | Prompt library (embedded + custom) | Must | 8 | Variables, versioning, per-type templates
F-041 | AI Engine | Skills system (inbuilt + custom) | Must | 13 | Skill = instructions + tools + output schema; enable/add
F-042 | AI Engine | AI agent teams / workflows | Should | 13 | Chain agents: research→outline→write→edit; tool calls
F-043 | AI Engine | AI usage & cost analytics | Should | 5 | Per-provider tokens, quota, cost dashboards
F-044 | Comprehensive Audit | Multi-source aggregation | Must | 13 | Merge SF + Ahrefs + Semrush + PSI + GSC + on-page
F-045 | Comprehensive Audit | Automated checklist engine | Must | 13 | 50+ checks: detector + data source + grade + owner
F-046 | Comprehensive Audit | PageSpeed / Core Web Vitals | Must | 8 | PSI desktop/mobile, LCP/CLS/INP, history
F-047 | Comprehensive Audit | GSC coverage/index issues | Must | 5 | 404/soft404/noindex/redirect/crawled-not-indexed
F-048 | Comprehensive Audit | Page-to-page + competitor audit | Should | 13 | Full-site & per-page vs competitors
F-049 | Comprehensive Audit | Auto SEO action plan | Must | 8 | Prioritized plan generated from findings
F-050 | Topical Content | Parent/child keyword clustering | Must | 8 | Topical map from seed keywords
F-051 | Topical Content | Content plan builder | Must | 8 | Pillar+cluster, briefs, internal-link map
F-052 | Topical Content | Landing page generator | Must | 5 | Copy + meta + schema per intent
F-053 | Topical Content | ReleVink AI placement finder | Should | 5 | Keyword/anchor → relevant pages
F-054 | Forms & Leads | Form builder + embed | Must | 8 | Contact/custom forms, validation, spam guard
F-055 | Forms & Leads | External form connectors | Should | 5 | Webhooks, native form platforms
F-056 | Forms & Leads | Onboarding/profiling capture | Should | 3 | who/what/source qualification
F-057 | Free Tools | Free tools suite + gating | Should | 13 | Domain age, broken link, link analyzer, dofollow/nofollow, website finder
F-058 | Free Tools | Public backlink monitor | Should | 5 | Lead-gen public tool
F-059 | Marketplace | Listings + filters + search | Should | 13 | DA/DR/AS, CF/TF, spam, category, country, price, bulk
F-060 | Marketplace | Cart, orders & fulfilment | Should | 13 | Guest post/link insertion, TAT, sample/report/block
F-061 | Marketplace | Wallet, funds & invoicing | Should | 8 | Balance, add funds, payouts, invoices
F-062 | Marketplace | Services catalog | Could | 5 | Link building, guest post, PR, niche edits, content, brand mentions
|  | TOTAL STORY POINTS |  | 494
Points by epic
| Epic | Points
| Platform | 32
| SEO Audit | 41
| Rank Tracker | 13
| Backlink CRM | 55
| Local SEO | 39
| AI Studio | 34
| Social | 26
| Leads/CRM | 24
| Reporting | 8
| Integrations | 11
| AI Engine | 52
| Comprehensive Audit | 60
| Topical Content | 26
| Forms & Leads | 16
| Free Tools | 18
| Marketplace | 39

## Database Schema
Database Schema (core tables)
PK = primary key (blue), FK = foreign key (teal). Time-series tables noted for ClickHouse.
Table | Column | Type | Key | Notes
organisation | id | uuid | PK | Tenant root
organisation | name | text
organisation | plan | text |  | essentials/advanced/enterprise
user | id | uuid | PK
user | organisation_id | uuid | FK | → organisation
user | email | citext |  | unique per org
user | role | text |  | owner/admin/manager/staff/client
project | id | uuid | PK
project | organisation_id | uuid | FK | → organisation
project | name | text
site | id | uuid | PK
site | project_id | uuid | FK | → project
site | domain | text
keyword | id | uuid | PK
keyword | project_id | uuid | FK | → project
keyword | phrase | text
keyword | country/lang | text |  | locale for SERP
rank_history | keyword_id | uuid | FK | → keyword — ClickHouse (time-series)
rank_history | checked_at | datetime |  | partition key
rank_history | position | int
audit_run | id | uuid | PK
audit_run | site_id | uuid | FK | → site
audit_run | score | numeric |  | 0-100 weighted
audit_issue | id | uuid | PK
audit_issue | audit_run_id | uuid | FK | → audit_run
audit_issue | rule | text
audit_issue | severity | text |  | + priority score
crawl_run | id | uuid | PK | scope/depth/robots
crawl_run | site_id | uuid | FK | → site
supplier | id | uuid | PK | backlink supplier
supplier | organisation_id | uuid | FK | → organisation
supplier | name/email/phone | text |  | contact + rating
supplier | country/niche | text
backlink | id | uuid | PK
backlink | project_id | uuid | FK | → project
backlink | target_site_id | uuid | FK | → site
backlink | supplier_id | uuid | FK | → supplier (nullable if free)
backlink | source_url/target_url | text
backlink | anchor_text | text
backlink | link_type | text |  | dofollow/nofollow/sponsored/ugc
backlink | paid_or_free | text
backlink | status | text |  | live/removed/changed/noindex/…
backlink | cost/currency | numeric
backlink | dr/da/authority | numeric |  | cached metrics
backlink | toxicity_score | numeric |  | 0-100 advisory
backlink | first_detected/last_verified | datetime
backlink_check_history | backlink_id | uuid | FK | → backlink — ClickHouse (time-series)
backlink_check_history | checked_at | datetime
backlink_check_history | http_status/rel/is_indexed | mixed |  | verification snapshot
backlink_file | id | uuid | PK | invoice/report/screenshot
backlink_file | backlink_id/supplier_id | uuid | FK | links to entity
credential | id | uuid | PK | vault reference only
credential | supplier_id/site_id | uuid | FK | subject of secret
credential | vault_ref | text |  | pointer to KMS/Vault; NO plaintext
gbp_location | id | uuid | PK | Google Business Profile
gbp_location | project_id | uuid | FK | → project
gbp_location | place_id/cid | text
gbp_review | location_id | uuid | FK | → gbp_location
gbp_post | location_id | uuid | FK | → gbp_location
grid_scan | id | uuid | PK | geo-grid run
grid_scan | keyword_id | uuid | FK | → keyword
grid_point | scan_id | uuid | FK | → grid_scan; lat/lng/position
content_item | id | uuid | PK
content_item | project_id | uuid | FK | → project
content_item | type/state/channel | text |  | state machine
content_version | content_item_id | uuid | FK | → content_item
schedule | content_item_id | uuid | FK | scheduled_at
publish_job | content_item_id | uuid | FK | idempotency_key
lead | id | uuid | PK
lead | project_id | uuid | FK | → project
lead | email/phone | text |  | dedupe keys
lead | utm_source/medium/campaign | text |  | attribution
lead | crm_contact_id | text |  | HubSpot id (nullable)
form | id | uuid | PK | source form
campaign | id | uuid | PK
activity_log | id | uuid | PK | immutable audit
activity_log | actor_id/action/target | mixed |  | who/what/when
ai_provider | id | uuid | PK | Claude/OpenAI/Perplexity/Gemini/custom
ai_provider | organisation_id | uuid | FK | → organisation
ai_provider | name/type/base_url | text |  | routing config
ai_provider | credential_id | uuid | FK | → credential (key in vault)
ai_provider | default_model/fallback_id | mixed |  | routing & fallback
prompt | id | uuid | PK | embedded or custom
prompt | organisation_id | uuid | FK | null = built-in/embedded
prompt | name/type/body | text |  | variables {{...}}
prompt | version/is_custom | mixed |  | versioned library
skill | id | uuid | PK | inbuilt or custom
skill | organisation_id | uuid | FK | null = inbuilt
skill | name/instructions | text |  | reusable instruction pack
skill | tools/output_schema | jsonb |  | tool refs + expected output
skill | is_custom/enabled | bool
agent | id | uuid | PK | member of a team
agent | organisation_id | uuid | FK | → organisation
agent | name/role | text |  | e.g. researcher/writer/editor
agent | provider_id | uuid | FK | → ai_provider
agent | skill_ids | uuid[] | FK | → skill (many)
agent_team | id | uuid | PK | workflow of agents
agent_team | steps | jsonb |  | ordered agent steps + routing
agent_run | id | uuid | PK | one execution
agent_run | agent_team_id | uuid | FK | → agent_team
agent_run | status/input/output | jsonb |  | trace, tokens, cost
ai_usage | provider_id | uuid | FK | → ai_provider — tokens/cost (ClickHouse)
audit_checklist_item | id | uuid | PK | catalog of checks
audit_checklist_item | code/category | text |  | e.g. TECH-01 / On-Page
audit_checklist_item | check/data_source | text |  | detector + SF/Ahrefs/Semrush/PSI/GSC
audit_checklist_item | severity/default_owner | text
audit_result | id | uuid | PK | result per run
audit_result | audit_run_id | uuid | FK | → audit_run
audit_result | checklist_item_id | uuid | FK | → audit_checklist_item
audit_result | grade/count/affected | mixed |  | pass/fail/partial + pages
audit_result | source_payload | jsonb |  | raw evidence from provider
pagespeed_result | site_id/url | uuid | FK | → site — PSI
pagespeed_result | device/lcp/cls/inp/score | mixed |  | Core Web Vitals (time-series)
gsc_issue | site_id | uuid | FK | → site — coverage/index issue
gsc_issue | type/count/status | mixed |  | 404/soft404/noindex/…
competitor | id | uuid | PK
competitor | project_id | uuid | FK | → project; domain
seo_plan | id | uuid | PK | generated action plan
seo_plan | project_id/audit_run_id | uuid | FK | prioritized tasks → task
topical_map | id | uuid | PK | from parent/child keywords
topical_map | project_id | uuid | FK | → project
topic_node | id | uuid | PK | pillar or cluster node
topic_node | topical_map_id/parent_id | uuid | FK | tree; keyword, intent, volume
content_plan | id | uuid | PK | pillar+cluster plan
content_plan | topical_map_id | uuid | FK | → topical_map; internal-link map
content_brief | content_plan_id/topic_node_id | uuid | FK | brief per node → content_item
form | org_id/project_id | uuid | FK | → project (builder)
form | schema/embed_code | jsonb |  | fields, validation, styling
form_submission | id | uuid | PK
form_submission | form_id | uuid | FK | → form; payload → lead
free_tool_lead | id | uuid | PK | captured via free tool
free_tool_lead | tool/input/email | mixed |  | domain-age/broken-link/… → lead
service | id | uuid | PK | catalog: link building, guest post, PR…
service | name/type/tags | text |  | most-popular/premium/etc.
marketplace_listing | id | uuid | PK | publisher inventory
marketplace_listing | domain/category/lang | text
marketplace_listing | da/dr/as/cf/tf/spam | numeric |  | authority & risk metrics
marketplace_listing | org_traffic/ref_domains | numeric
marketplace_listing | guest_post_price/link_ins_price | numeric
marketplace_listing | link_type/link_validity/tat | mixed |  | order terms
order | id | uuid | PK | marketplace/service order
order | organisation_id | uuid | FK | → organisation
order | listing_id/service_id | uuid | FK | what was ordered
order | status/amount/tat_due | mixed |  | cart→paid→in-progress→delivered
order | backlink_id | uuid | FK | → backlink (on delivery)
wallet | organisation_id | uuid | FK | → organisation; balance
wallet_txn | wallet_id/type/amount | mixed |  | add-funds/charge/payout/invoice

## API Integrations
API Integrations
External providers wrapped in uniform connectors (auth/fetch/publish/health).
Provider | Category | Purpose | Auth | Quota / cost concern | Phase
Claude (Anthropic) | AI | Content, briefs, audit recommendations, review replies | API key | Token cost — cache & batch | 4
Ahrefs | SEO data | Backlinks, keywords, domain metrics | API key | Costly — schedule & cache | 2
Semrush | SEO data | Toxic score, positions, backlinks | API key | Row limits per plan | 2
Google Search Console | SEO data | Clicks, impressions, queries | OAuth2 | Per-property; sampling | 1
Google Business Profile | Local | Locations, reviews, posts, publishing | OAuth2 | Rate limits; review policies | 3
Google Maps / Places | Local | Geo-grid SERP, place data | API key | Per-request billing | 3
Google Analytics 4 | Analytics | Traffic & conversions | OAuth2 | API quotas | 1
Google Ads | Ads | Campaign & lead data | OAuth2 | Dev token approval | 6
Meta (Facebook/Instagram) | Social | Publish, page/ads insights, lead ads | OAuth2 | App review; IG publish rules | 5
LinkedIn | Social | Publish, lead gen forms | OAuth2 | Restricted scopes | 5
X (Twitter) | Social | Publish, analytics | OAuth2 | Tiered rate limits | 5
Microsoft Ads / Bing WMT | SEO/Ads | Webmaster & ads data | OAuth2 | — | 6
HubSpot | CRM | Contacts, deals, forms (two-way) | OAuth2 | API daily limits | 6
Calendly | CRM | Booking links & events | OAuth2/API | Webhook-driven | 6
Microsoft Teams | Notify | Channels, alerts, reports | OAuth2 / webhook | Message throttling | 6
Screaming Frog | Crawl | Crawl data (self-hosted CLI) | License/CLI | Self-hosted resource | 1
Xero / MYOB / QuickBooks | Billing | Accounting add-on | OAuth2 | Optional add-on | 6
Looker Studio | Reporting | Embedded dashboards | OAuth2 | — | 1
OpenAI (ChatGPT) | AI | Alt content/agent provider in AI hub | API key | Token cost — routed | 4
Perplexity | AI | Research/answer agent in AI hub | API key | Token cost — routed | 4
Google Gemini | AI | Alt content/multimodal provider | API key | Token cost — routed | 4
Google PageSpeed Insights | SEO data | Speed + Core Web Vitals for audit | API key | Per-request; batch | 1
Payment gateway (Stripe) | Billing | Wallet, add-funds, marketplace orders | API key | PCI via provider | 6

## Roadmap
Delivery Roadmap
Phased plan. Edit the blue 'Weeks' cells; total is a live SUM. Phases 2 & 3 can partly parallelize.
Phase | Focus | Key deliverables | Squad | Depends on | Weeks
0. Foundation | Platform core | Auth/RBAC, tenancy, projects, tasks, time, queue, CI/CD, observability | Platform | — | 5
1. SEO Core & Audit | Rank & audit | Rank tracker, crawl, multi-source audit (SF+Ahrefs+Semrush+PSI+GSC), checklist engine, SEO plan, reports | SEO | Phase 0 | 9
2. Backlink CRM | Differentiator | Backlink DB, supplier CRM, live/removed verify, files, toxic, vault | Backlink | Phase 0 | 9
3. Local SEO | Differentiator | GMB/GBP audit, category, review/post audit, geo-grid Teleport, Website↔GBP | Local | Phase 1 | 9
4. AI Engine & Studio | AI + content | AI provider hub, prompt library, skills, agent teams; content state machine + generators, topical map, content plan, image gen | AI | Phase 0 | 10
5. Social & Automation | Publish | Connectors, calendar, scheduler, bulk gen+schedule, alerts, report automation | Growth | Phase 4 | 7
6. Leads, Marketplace & Integrations | Growth | Forms & lead capture, attribution, HubSpot, Calendly, Teams, free tools, services & backlink marketplace, wallet, white-label | Growth | Phase 1 | 9
|  |  |  | Sequential total (weeks) | 58
|  |  |  | With 2 squads in parallel (est.) | 41

## Audit Checklist
Automated SEO Audit Checklist
Every check maps to a data source and runs automatically. Findings feed the SEO Action Plan. Built from the client checklists.
Code | Category | Check | Data source | Auto | Severity | Fix owner
CHK-01 | Indexation | Important pages are indexed / not missing from index | GSC + Screaming Frog | Y | High | SEO Tech
CHK-02 | Indexation | Pages indexed that shouldn't be (index bloat) | GSC + Crawler | Y | Med | SEO Tech
CHK-03 | Indexation | Noindex on pages that should rank | Screaming Frog | Y | High | SEO Tech
CHK-04 | Indexation | Pages blocked by robots.txt that should be indexed | GSC + robots parse | Y | High | Web Dev
CHK-05 | Indexation | robots.txt exists and references sitemap | robots parse | Y | Low | SEO Tech
CHK-06 | Indexation | XML & HTML sitemaps exist and submitted to GSC | GSC + Crawler | Y | Med | SEO Tech
CHK-07 | Indexation | Sitemaps contain only valid, indexable URLs | Crawler + Sitemap crawl | Y | Med | SEO Tech
CHK-08 | Indexation | Soft 404 / error pages returning 200 | GSC + Crawler | Y | Med | Web Dev
CHK-09 | Indexation | Crawled / Discovered — currently not indexed | GSC | P | Med | SEO Tech
CHK-10 | Crawlability | Important content within ~4 clicks of home | Crawler (depth) | Y | Med | SEO
CHK-11 | Crawlability | Pages with >300 outlinks | Crawler (outlinks) | Y | Low | SEO
CHK-12 | Crawlability | Internal links to 4XX/5XX URLs | Crawler | Y | High | Web Dev
CHK-13 | Crawlability | Orphan pages (no internal links in) | Crawler (link graph) | Y | Med | SEO
CHK-14 | Crawlability | Site reachable / not timing out / not down | Crawler (status) | Y | High | Web Dev
CHK-15 | On-Page | Missing page titles | Crawler | Y | High | SEO Tech
CHK-16 | On-Page | Duplicate page titles | Crawler | Y | High | SEO Tech
CHK-17 | On-Page | Titles over ~60–65 characters | Crawler | Y | Low | SEO Tech
CHK-18 | On-Page | Missing meta descriptions | Crawler | Y | Med | SEO Tech
CHK-19 | On-Page | Duplicate meta descriptions | Crawler | Y | Med | SEO Tech
CHK-20 | On-Page | Missing H1 | Crawler | Y | High | SEO Tech
CHK-21 | On-Page | Duplicate / multiple H1 | Crawler | Y | Med | SEO Tech
CHK-22 | On-Page | Heading hierarchy (H1/H2/H3) correct | Crawler | P | Low | SEO Tech
CHK-23 | On-Page | Missing image ALT text | Crawler | Y | Med | SEO Tech
CHK-24 | On-Page | SEO-friendly, clean URL structure | Crawler | P | Med | Web Dev
CHK-25 | On-Page | tel: / mailto: tags present where relevant | Crawler | Y | Low | Web Dev
CHK-26 | Content | Internal duplicate content | Crawler (body hash) | Y | High | Content
CHK-27 | Content | External duplicate / scraped content | Semrush/Ahrefs + AI | P | Med | Content
CHK-28 | Content | Thin content pages | Crawler + AI | P | Med | Content
CHK-29 | Content | Keyword cannibalisation | Rankings + AI | P | Med | SEO
CHK-30 | Content | Keyword density positive/negative | Crawler + AI | P | Low | Content
CHK-31 | Technical | HTTPS everywhere; no insecure pages w/ SSL | Crawler | Y | High | Web Dev
CHK-32 | Technical | HTTP and HTTPS both serve (protocol dup) | Crawler | Y | High | Web Dev
CHK-33 | Technical | Canonical tags present & correct | Crawler | Y | High | SEO Tech
CHK-34 | Technical | Redirect chains / loops | Crawler (reports) | Y | Med | Web Dev
CHK-35 | Technical | Non-301 (302/307) / JS / meta-refresh redirects | Crawler | Y | Med | Web Dev
CHK-36 | Technical | Broken outbound links | Crawler | Y | Med | Web Dev
CHK-37 | Technical | 404 errors | Crawler + GSC | Y | Med | Web Dev
CHK-38 | Technical | Intrusive interstitials / aggressive pop-ups | Manual + AI | P | Med | UX
CHK-39 | Rendering | Content visible with JS rendering | Crawler (render) | Y | High | Web Dev
CHK-40 | Rendering | Crucial content not in iframe / Flash | Crawler | Y | Med | Web Dev
CHK-41 | Rendering | Cache / rendering issues per URL | Crawler + PSI | P | Low | Web Dev
CHK-42 | Speed & CWV | Loads under 3s (desktop & mobile) | PageSpeed Insights | Y | High | Web Dev
CHK-43 | Speed & CWV | Core Web Vitals: LCP / CLS / INP pass | PageSpeed Insights | Y | High | Web Dev
CHK-44 | Speed & CWV | GZIP / Brotli compression enabled | PSI + Crawler | Y | Low | Web Dev
CHK-45 | Speed & CWV | CSS / JS minified | PSI + Crawler | Y | Low | Web Dev
CHK-46 | Speed & CWV | Images compressed / next-gen formats | PSI | Y | Med | Web Dev
CHK-47 | Mobile | Mobile-friendly / responsive on all devices | PSI + Crawler | Y | High | Web Dev
CHK-48 | Mobile | Legible fonts & tappable targets | PSI | P | Low | UX
CHK-49 | Mobile | Mobile parity with desktop (links/content) | Crawler (UA) | P | Med | Web Dev
CHK-50 | Structured Data | Schema present on key templates | Crawler + Rich Results | Y | Med | SEO Tech
CHK-51 | Structured Data | Schema errors / not spammy | Crawler + Rich Results | Y | Med | SEO Tech
CHK-52 | International | hreflang implemented & reciprocal | Crawler | Y | Med | SEO Tech
CHK-53 | International | GSC international targeting set | GSC | P | Low | SEO
CHK-54 | Off-Page | Backlink profile & referring domains | Ahrefs + Semrush | Y | Med | SEO
CHK-55 | Off-Page | Toxic backlinks flagged | Semrush + engine | Y | High | SEO
CHK-56 | Off-Page | Lost / removed links | Ahrefs + Backlink CRM | Y | Med | SEO
CHK-57 | Off-Page | Link intersect vs competitors (gaps) | Ahrefs | P | Med | SEO
CHK-58 | Setup | Analytics (GA4) installed | Crawler + GA | Y | High | Web Dev
CHK-59 | Setup | Search Console verified & connected | GSC | Y | High | Web Dev
CHK-60 | Setup | Social profiles linked on site | Crawler | Y | Low | SEO
CHK-61 | Setup | Google Map linked (contact/footer) | Crawler | Y | Low | SEO
CHK-62 | Local | GBP complete & NAP consistent with site | GBP + Crawler | Y | High | SEO
Auto: Y = fully automated via data source · P = partly automated / AI-assisted. Grades per run: Pass / Fail / Partial. Findings auto-generate the prioritized SEO Action Plan and tasks.

## Pricing Matrix
Pricing Feature Matrix
Tier availability (from reference screenshots). ✔ included · limits shown · — not included.
Feature | Essentials | Advanced | Enterprise
Companies / Contacts | Unlimited | Unlimited | Unlimited
Dashboard | ✔ | ✔ | ✔
Roles & Permissions | ✔ | ✔ | ✔
Staff Users | Unlimited | Unlimited | Unlimited
Activity Logs | ✔ | ✔ | ✔
File Storage | 1 GB | 10 GB | Custom
All Integrations (Google/Meta/Bing…) | ✔ | ✔ | ✔
Rank Tracker keywords | 250 / mo | 500 / mo | Custom
Local Rank Tracker credits | 100 / mo | 250 / mo | Custom
SEO Audit pages | 250 / mo | 5000 / mo | Custom
Audit frequency | Real-time only | Real-time + automated | Custom
Report export (Excel/PDF) | ✔ | ✔ | ✔
Accounting (Xero/MYOB/QuickBooks) | Add-on | Add-on | Add-on
API Access | — | — | ✔
Projects / Tasks | Unlimited | Unlimited | Unlimited
Multiple assignee / filters / bulk | ✔ | ✔ | ✔
Kanban & List views | ✔ | ✔ | ✔
Looker Studio & custom reporting | ✔ | ✔ | ✔
Schedule reports | — | ✔ | ✔
Report branding (logo) | ✔ | ✔ | ✔
Report white-label | — | ✔ | ✔
Client user access | — | — | ✔
Support: Email | ✔ | ✔ | ✔
Support: Chat | — | — | ✔
Onboarding training | — | ✔ | ✔
Knowledge base / LMS / Zoom | ✔ | ✔ | ✔

## Cost Estimate
Effort & Cost Estimate
EDIT the blue cells (weeks, devs, hrs/wk, blended rate). Everything else is a formula.
Assumptions
Hours / dev / week | 32
Blended rate (per hour) | 55
Phase | Weeks | Devs | Dev-weeks | Hours | Cost
0. Foundation | 5 | 3 | 15 | 480 | 26400
1. SEO Core & Audit | 9 | 3 | 27 | 864 | 47520
2. Backlink CRM | 9 | 3 | 27 | 864 | 47520
3. Local SEO | 9 | 3 | 27 | 864 | 47520
4. AI Engine & Studio | 10 | 3 | 30 | 960 | 52800
5. Social & Automation | 7 | 2 | 14 | 448 | 24640
6. Leads, Marketplace & Integrations | 9 | 3 | 27 | 864 | 47520
QA / DevOps / PM (overlay) | 24 | 2 | 48 | 1536 | 84480
TOTAL |  |  | 215 | 6880 | 378400
Contingency % | 15%
GRAND TOTAL (incl. contingency) |  |  |  |  | 435160
Note: rate is an illustrative placeholder — replace $B$6 with your actual blended rate. Estimate assumes overlapping phases with 2–3 squads; sequential calendar time is shorter than the sum of dev-weeks.